## Project Overview
Field | Details
Project Name | JobMatch AI - Personal Intelligent Job Discovery System
Owner | Omkar (Personal Use)
Goal | Automatically find and rank relevant jobs from target companies based on resume/skills
Start Date | June 2026
Target MVP | 4 Weeks
Budget | Free (self-hosted: Ollama, n8n, Qdrant, SQLite/Postgres)
Primary Stack | Node.js, Python, n8n, Ollama, Qdrant, Cheerio/BeautifulSoup
Notification | Email (Gmail) / Telegram (Phase 1)
Job Sources (Phase 1) | Company career pages from AmbitionBox company list
Job Sources (Phase 2) | Naukri/LinkedIn job alert emails via IMAP
Resume Value | Demonstrates scraping, automation, RAG, vector search, local LLM
GitHub Repo | Scarpping folder - publish as public portfolio repo
Success Metrics | Daily top 5-10 relevant jobs; reduced manual search time; interview callbacks

## Phase Plan
Phase | Week | Focus | Deliverables | Status
Phase 0 - Setup | Week 0 | Environment & repo setup | Docker (n8n, Ollama, Qdrant), GitHub repo, folder structure | In Progress
Phase 1 - Data Collection | Week 1 | Company & job ingestion | AmbitionBox company CSV, career URL finder, job scraper, SQLite DB | Planned
Phase 2 - AI Matching | Week 2 | Resume + vector search | Resume parser, Ollama embeddings, Qdrant index, similarity match | Planned
Phase 3 - RAG Ranking | Week 3 | LLM reranking | Ollama prompt for top job ranking with match reason & missing skills | Planned
Phase 4 - Automation | Week 3-4 | n8n workflows | Daily cron: scrape -> match -> notify pipeline | Planned
Phase 5 - Alerts | Week 4 | Notifications | Email/Telegram daily digest of top matched jobs | Planned
Phase 6 - Portfolio | Week 4 | Documentation | README, architecture diagram, demo video, resume bullets | Planned
Phase 7 - Enhance | Later | Email alert ingestion | Parse Naukri/LinkedIn alert emails into same pipeline | Backlog
Phase 8 - UI | Later | Dashboard | Simple web UI: matches, applied jobs, saved companies | Backlog

## Task Breakdown
ID | Phase | Task | Description | Tech/Tools | Priority | Est. Hours | Week | Status | Dependencies
T01 | Phase 0 | Create project folder structure | scraper/, matcher/, n8n/, docs/, data/ | Git | High | 2 | 0 | In Progress | -
T02 | Phase 0 | Docker Compose setup | n8n + Ollama + Qdrant containers | Docker | High | 4 | 0 | Planned | T01
T03 | Phase 0 | Install Ollama models | Pull llama3.2 and nomic-embed-text | Ollama | High | 1 | 0 | Planned | T02
T04 | Phase 1 | Scrape AmbitionBox companies | Filtered IT companies Mumbai/Pune - CSV output | Node.js/Cheerio | High | 4 | 1 | Done | -
T05 | Phase 1 | Design database schema | companies, jobs, resume_chunks, matches tables | SQLite/Postgres | High | 3 | 1 | Planned | T04
T06 | Phase 1 | Career page URL finder | Resolve career/jobs URL per company | Node.js | High | 6 | 1 | Planned | T04
T07 | Phase 1 | Career page job scraper | Extract title, location, description, apply URL | Node.js/Cheerio | High | 8 | 1 | Planned | T06
T08 | Phase 1 | Job deduplication logic | Unique by URL + company + title hash | Node.js | Medium | 3 | 1 | Planned | T07
T09 | Phase 2 | Resume input & parsing | PDF/text resume to structured sections | Python/Node | High | 5 | 2 | Planned | T05
T10 | Phase 2 | Chunk resume text | Split into skills, experience, projects, education | Custom | High | 2 | 2 | Planned | T09
T11 | Phase 2 | Generate embeddings | Ollama nomic-embed-text for resume & jobs | Ollama API | High | 4 | 2 | Planned | T10
T12 | Phase 2 | Qdrant collections setup | jobs collection + resume_chunks collection | Qdrant | High | 4 | 2 | Planned | T11
T13 | Phase 2 | Similarity search | Top 20 jobs per user resume vector | Qdrant | High | 4 | 2 | Planned | T12
T14 | Phase 3 | LLM rerank prompt | Score jobs 0-100 with fit reason & gaps | Ollama llama3.2 | High | 4 | 3 | Planned | T13
T15 | Phase 3 | Filter low matches | Only send jobs with score > 70 | Custom | Medium | 2 | 3 | Planned | T14
T16 | Phase 4 | n8n daily cron workflow | Schedule trigger at 8 AM daily | n8n | High | 3 | 3 | Planned | T07,T13
T17 | Phase 4 | n8n scrape workflow | Loop companies, fetch jobs, save to DB | n8n HTTP+Code | High | 6 | 3 | Planned | T16
T18 | Phase 4 | n8n match workflow | Embed new jobs, vector search, LLM rank | n8n+Ollama | High | 6 | 4 | Planned | T17
T19 | Phase 5 | Email digest template | HTML/text email with top 5-10 jobs | Gmail SMTP | High | 3 | 4 | Planned | T18
T20 | Phase 5 | Telegram bot alerts | Optional free WhatsApp alternative | Telegram Bot API | Medium | 3 | 4 | Planned | T18
T21 | Phase 6 | Write README | Setup, architecture, screenshots, how to run | Markdown | High | 4 | 4 | Planned | T19
T22 | Phase 6 | Record demo video | 2-3 min walkthrough for portfolio | Screen recorder | Medium | 2 | 4 | Planned | T21
T23 | Phase 6 | Resume & LinkedIn bullets | Project description for job applications | Docs | High | 2 | 4 | Planned | T21
T24 | Phase 7 | IMAP email alert parser | Ingest Naukri/LinkedIn alert emails | n8n IMAP | Low | 6 | Later | Backlog | T18
T25 | Phase 8 | Simple dashboard UI | View matches, mark applied, save jobs | React/HTML | Low | 10 | Later | Backlog | T18

## Tech Stack
Layer | Tool | Purpose | Cost | Notes
Scraping | Node.js + Cheerio | Fetch & parse company/job HTML | Free | Already built for AmbitionBox
Scraping | Python + BeautifulSoup | Alternative scraper scripts | Free | Optional
Automation | n8n (self-hosted) | Daily workflows, cron, integrations | Free | Docker on local machine
LLM | Ollama (llama3.2) | Job ranking, explanations | Free | Runs locally, no API cost
Embeddings | Ollama (nomic-embed-text) | Vectorize resume & job text | Free | 768-dim embeddings
Vector DB | Qdrant | Similarity search for job matching | Free | Docker container
Database | SQLite / PostgreSQL | Companies, jobs, matches, history | Free | Start SQLite, migrate later
Notifications | Gmail SMTP | Daily job digest email | Free | Personal Gmail
Notifications | Telegram Bot | Instant job alerts | Free | Easier than WhatsApp
Container | Docker Compose | Run all services together | Free | n8n + Ollama + Qdrant
Version Control | GitHub | Portfolio repo | Free | Public repo with README

## Milestones
# | Milestone | Target Week | Criteria (Done When) | Status
1 | Company list ready | Week 1 | CSV with 500+ companies name, slug, profile URL | Done
2 | First jobs scraped | Week 1 | At least 50 jobs from 10 company career pages in DB | Planned
3 | Resume indexed | Week 2 | Resume chunks stored with embeddings in Qdrant | Planned
4 | First match run | Week 2 | Top 20 jobs returned by vector similarity | Planned
5 | LLM ranking works | Week 3 | Ollama returns ranked jobs with fit explanation | Planned
6 | n8n pipeline live | Week 3 | Daily automated scrape + match without manual run | Planned
7 | First daily alert | Week 4 | Receive email/Telegram with top 5 matched jobs | Planned
8 | Portfolio ready | Week 4 | GitHub README + demo + resume bullets complete | Planned
9 | First real application | Week 4+ | Apply to a job found by the system | Planned
10 | Interview mention | Ongoing | Explain project clearly in at least 1 interview | Planned

## Weekly Schedule
Week | Mon-Tue | Wed-Thu | Fri-Sat | Sun | Goal
Week 1 | DB schema + career URL finder | Career page scraper | Test on 20 companies | Fix bugs, CSV export | Jobs in database
Week 2 | Resume parser + chunking | Ollama embeddings setup | Qdrant indexing | Test similarity search | Matching works
Week 3 | LLM rerank prompt tuning | n8n scrape workflow | n8n match workflow | End-to-end test | Automation works
Week 4 | Email/Telegram alerts | README + architecture doc | Demo video | Apply to jobs using tool | MVP complete